## How to use
Instructions: Fill in the rows and columns in the next tab with your line item details. Keep the header row intact. Epic and Stage names must match existing values in the estimate. Below is the definition for each factor
Estimating Factors | Definition | Metrics
Base Hours | Expected number of hours based on a single factor | Base Hours | Size | Complexity
Factor | Number of times the task needs to be done | 1-2 | very small | very simple
Rate | Resources hourly rate | 3-5 | small | simple
Size | Defines the expected size of the effort: very small, small, medium, large, very large | 6-8 | medium | medium
Complexity | Defines how difficult the task is expected to be: very simple, simple, medium, complex, very complex | 9-12 | large | complex
Confidence | Defines how confident the estimator is on accomplishing the task based on background information: high, medium, low | 13-15 | very large | very complex

## Line Items Template
Grameen
Epic Name | Stage Name | Workstream | Week # | Description | Category | Resource | Base Hours | Factor | Rate | Cost Rate | Size | Complexity | Confidence | Comments | Adjusted Hours | Total Amount | Total Cost | Margin | Margin %
Phase 0 | Internal Prep | PM | 0 | Create Project Plan |  |  | 4 | 1 | 200 |  | small | simple | high | Develop comprehensive project plan with phases, tasks, and timelines
Phase 0 | Internal Prep | PM | 0 | Kickoff Meeting Prep |  |  | 6 | 1 | 200 |  | small | simple | high | Client Program Kickoff Deck Creation/Review/Revise
Phase 0 | Internal Prep | PM | 0 | Team Alignment |  |  | 2 | 1 | 200 |  | small | simple | high | Assign roles, review deck, confirm delivery approach
Phase 0 | Internal Prep | Content Team | 0 | Content Creation |  |  | 20 | 1 | 200 |  | medium | medium | medium | Develop curriculum, modules, exercises, assessments
Phase 0 | Internal Prep | All | 0 | Internal Review |  |  | 1 | 1 | 200 |  | small | simple | high | Review and revise for client presentation
Phase 0 | Internal Prep | All | 0 | Client Review |  |  | 2 | 1 | 200 |  | small | simple | high | Present content to Grameen, gather feedback
Phase 0 | Internal Prep | All | 0 | Finalization & Approval |  |  | 4 | 1 | 200 |  | small | simple | medium | Incorporate feedback and finalize content
Phase 0 | Internal Prep | Delivery | 0 | Initial Scheduling |  |  | 4 | 1 | 200 |  | small | medium | medium | Draft training calendar and delivery waves
Phase 0 | Internal Prep | All | 0 | Select LMS/Modality |  |  | 2 | 1 | 200 |  | small | medium | medium | Plan for LMS or training delivery platform and modality
Phase 0 | Internal Prep | All | 0 | Design Delivery Methods |  |  | 2 | 1 | 200 |  | small | medium | medium | Plan for live, virtual, and e-learning formats
Phase 1 | Leadership & Pilot Rollout | All | 1 | Branch Visit |  |  | 6 | 1 | 200 |  | small | medium | low | "eye in the sky" onsite visit
Phase 1 | Leadership & Pilot Rollout | Tech/PM | 1 | Success Metrics |  |  | 6 | 1 | 200 |  | small | medium | medium | Set up Success Metric Tracking Tactics
Phase 1 | Leadership & Pilot Rollout | Content Team | 1 | Leadership Workshop |  |  | 6 | 1 | 200 |  | medium | simple | high | Deliver executive training, gather feedback
Phase 1 | Leadership & Pilot Rollout | Content Team | 1 | Pilot Cohort Selection |  |  | 2 | 1 | 200 |  | small | simple | high | Identify staff champions for pilot
Phase 1 | Leadership & Pilot Rollout | Content Team | 1 | Pilot Training Delivery |  |  | 12 | 1 | 200 |  | medium | medium | high | Run pilot sessions, collect feedback
Phase 1 | Leadership & Pilot Rollout | All | 1 | Program Refinement |  |  | 6 | 1 | 200 |  | small | medium | high | Adjust curriculum based on pilot
Phase 1 | Leadership & Pilot Rollout | PM | 1 | Progress Reporting |  |  | 2 | 1 | 200 |  | small | simple | high | Summarize pilot outcomes, lessons learned
Phase 2 | Permit License | PM | 2 | Scheduling & Logistics |  |  | 8 | 1 | 200 |  | small | simple | high | Coordinate sessions by region/department
Phase 2 | Permit License | All | 2 | Training Delivery |  |  | 16 | 1 | 200 |  | small | medium | high | Facilitate live/virtual sessions
Phase 2 | Permit License | Content Team | 2 | Knowledge Checks |  |  | 6 | 1 | 200 |  | small | simple | high | Assess learning and issue credentials
Phase 2 | Permit License | PM | 2 | Attendance Tracking |  |  | 6 | 1 | 200 |  | small | simple | high | Monitor completions and follow-up
Phase 2 | Permit License | PM | 2 | Feedback Collection |  |  | 4 | 1 | 200 |  | small | simple | high | Gather participant feedback
Phase 3 | Standard License | All | 3 | Advanced Cohort Selection |  |  | 2 | 1 | 200 |  | small | simple | high | Identify AI Champions and technical teams
Phase 3 | Standard License | All | 3 | CDL Training Delivery |  |  | 8 | 1 | 200 |  | small | medium | high | Departmental automation workshops
Phase 3 | Standard License | All | 3 | Pilot License Training |  |  | 8 | 1 | 200 |  | small | medium | high | AI developer/agentic workshops
Phase 3 | Standard License | All | 3 | Use-case Ideation |  |  | 6 | 1 | 200 |  | small | medium | high | Facilitate real-world AI project development
Phase 3 | Standard License | All | 3 | Progress Reporting |  |  | 2 | 1 | 200 |  | small | simple | high | Summarize advanced tier outcomes
Phase 4 | Train-the-Trainer | All | 4 | TTT Workshop |  |  | 8 | 1 | 200 |  | medium | medium | high | Conduct train-the-trainer sessions
Phase 4 | Train-the-Trainer | Content Team | 4 | Shadowing & Co-Facilitation |  |  | 8 | 1 | 200 |  | medium | medium | high | Internal trainers co-lead sessions
Phase 4 | Train-the-Trainer | Content Team | 4 | Certification |  |  | 2 | 1 | 200 |  | small | simple | high | Certify internal trainers
Phase 5 | Project Closure | All | 5 | Q&A Support |  |  | 6 | 1 | 200 |  | small | simple | high | Answer post-training questions
Phase 5 | Project Closure | All | 5 | Usage Monitoring |  |  | 4 | 1 | 200 |  | small | simple | high | Track AI tool adoption and incidents
Phase 5 | Project Closure | All | 5 | Success Metrics Reporting |  |  | 2 | 1 | 200 |  | small | simple | high | Report on certification and adoption