## Line Items Template
Estimate Line Items Template
Instructions: Fill in the rows below with your line item details. Keep the header row intact. Epic and Stage names must match existing values in the estimate.
Epic Name | Stage Name | Workstream | Week # | Description | Category | Base Hours | Factor | Rate | Size | Complexity | Confidence | Comments | Adjusted Hours | Total Amount
1 | 0-Pre Kick-off Prep | All | 0 | Project Kick-off Prep |  | 15 | 1 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 1 | Data & Content location & Inventory Discovery, Document |  | 20 | 2 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 1 | Exec Interviews |  | 2 | 2 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 1 | Interviews |  | 2 | 2 | 400 | small | small | high | Team will need to draft all deliverables as we go through the initial weeks effort gathering data
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 1 | Deliverable Development |  | 2 | 1 | 400 | small | small | high | Is steerco part of kickoff? if not we need a seperate meet to set expectations, rules of operation
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 1 | Deliverable Iteration |  | 4 | 1 | 400 | small | small | high | Add details about the who for interviews being planned
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 1 | Interviews |  | 2 | 2 | 400 | small | small | high | Move 1:1 and exec intervies to follow the group DLT and information gathering
1 | 1-Empathize -Discovery & Alignment | All | 1 | SteerCo Selection and Format |  | 2 | 1 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | B-AI Readiness & Use Case | 1 | Interviews |  | 2 | 6 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 2 | Workshops Leaders |  | 3 | 1 | 400 | small | small | high | Exec interviews should be to confirm the information we have gathered, nit get new data
1 | 1-Empathize -Discovery & Alignment | A-Content Governance/IA | 2 | Workshops Users |  | 3 | 1 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | B-AI Readiness & Use Case | 2 | Deliverable Development |  | 6 | 1 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | B-AI Readiness & Use Case | 2 | Deliverable Iteration |  | 4 | 1 | 400 | small | small | high
1 | 1-Empathize -Discovery & Alignment | B-AI Readiness & Use Case | 2 | Workshop |  | 4 | 6 | 400 | small | small | high | 3 people
1 | 1-Empathize -Discovery & Alignment | B-AI Readiness & Use Case | 2 | Discovery Research |  | 12 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 2 | Develop SteerCo |  | 4 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 2 | PEA Business Strategy Discovery |  | 24 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 3 | Site taxonomy development |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 3 | Classification engine |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 3 | Education Workshop |  | 4 | 2 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 3 | Business Case Development WS |  | 12 | 2 | 400 | small | small | high
1 | 2-Define-IA/AI Design | C-Tenant Realignment | 3 | Classification engine criteria |  | 4 | 1 | 400 | small | small | high | Need output formats, reviews, pre reads etc
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 4 | Site taxonomy development |  | 12 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 4 | Compliance/GRC design |  | 12 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 4 | Classification design |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 4 | Priorities Workshop |  | 6 | 2 | 400 | small | small | high
1 | 2-Define-IA/AI Design | C-Tenant Realignment | 4 | Detailed site catalog and selection criteria |  | 4 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 5 | IA Design |  | 8 | 1 | 400 | small | small | high | This will be tough to be successful at this early and without enough data, I think this is too early
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 5 | GRC Policy Development |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 5 | Autoclassification Use Cases |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 5 | AI-IA Mapping |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 5 | IA prototype plan |  | 4 | 2 | 400 | small | small | high | Let's do this and the design together, up the hours as well
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 5 | Classification prototype plan |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | A-Content Governance/IA | 5 | GRC prototype policy doc |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 6 | Pilot Curriculum Desgin |  | 8 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 6 | Pilot Cohort Recruit |  | 4 | 1 | 400 | small | small | high
1 | 2-Define-IA/AI Design | B-AI Readiness & Use Case | 6 | Draft AI Pilot Plan |  | 8 | 1 | 400 | small | small | high
1 | 3-Prototype | A-Content Governance/IA | 6 | GRC policy test implementation |  | 8 | 1 | 400 | small | small | high
1 | 3-Prototype | A-Content Governance/IA | 6 | Classification imp,enmtqtion |  | 8 | 1 | 400 | small | small | high
1 | 3-Prototype | A-Content Governance/IA | 7 | IA testing |  | 8 | 1 | 400 | small | small | high
1 | 3-Prototype | A-Content Governance/IA | 7 | Classification testing |  | 8 | 1 | 400 | small | small | high
1 | 5-Deliverables and Handover | A-Content Governance/IA | 7 | Implement IA GRC Classification |  | 8 | 1 | 400 | small | small | high
1 | 5-Deliverables and Handover | A-Content Governance/IA | 7 | Document new IA |  | 8 | 1 | 400 | small | small | high
1 | 4-Pilot | D-AI Pilot | 8 | Weekly Pilot Curriculum |  | 8 | 1 | 400 | small | small | high
1 | 4-Pilot | D-AI Pilot | 9 | Weekly Pilot Curriculum |  | 8 | 1 | 400 | small | small | high
1 | 4-Pilot | D-AI Pilot | 10 | Weekly Pilot Curriculum |  | 8 | 1 | 400 | small | small | high
1 | 4-Pilot | D-AI Pilot | 11 | Weekly Pilot Curriculum |  | 8 | 1 | 400 | small | small | high
1 | 5-Deliverables and Handover | A-Content Governance/IA | 12 | Executive overview and decsion matrix |  | 4 | 1 | 400 | small | small | high | I also would make sure we're not waiting until week 9 for exec decisions, they need to come along on the journey and direct the actions
1 | 5-Deliverables and Handover | B-AI Readiness & Use Case | 12 | Deliverables |  | 12 | 1 | 400 | small | small | high
1 | 5-Deliverables and Handover | B-AI Readiness & Use Case | 12 | SteerCo review |  | 4 | 4 | 400 | small | small | high | steerco week 1,4, 8, 12
1 | 5-Deliverables and Handover | B-AI Readiness & Use Case | 12 | Exec overview and production AI plan |  | 8 | 1 | 400 | small | small | high
1 | 5-Deliverables and Handover | D-AI Pilot | 12 | Document results |  | 4 | 1 | 400 | small | small | high
1 | 5-Deliverables and Handover | D-AI Pilot | 12 | Review findings with team |  | 2 | 1 | 400 | small | small | high