## Risks
Risk ID | Status (*) | Date Opened | Risk Description and Impact Effect | Risk Probability | Risk Impact | Risk Score (calc) | Exposure (calc) | Risk Response Strategy (*) | Mitigation Response (Contingency Plan) / Action Log | Next Steps | Owner | Due Date | LOOKUP FIELDS
1
4
2
3
Note on E1: A subjective assessment of the likelihood that the risk will materialize. This should be completed by the Risk Manager (i.e. in most cases the Project Manager), with input from the appropriate team leaders. The selection options are as follows: High Medium, Low
Note on F1: Based on a subjective assessment by the Risk Manager (i.e. Project Manager), with input from the appropriate team leaders, and is one of the following categories: High, Medium, and Low.
Note on G1: The product of the risk probability and the risk impact with values ranging from 1 to 9.
Note on H1: Exposure rating of the risk. The risk exposure is set to the following: Green for risk scores of 1,2, Yellow for risk scores of 3,4, and Red for risk scores of 6,9.
Note on I1: Actionable response to the risk. Mitigation strategies are required for yellow and red risk exposures. Selection options are listed in the dropdown list.

## Issues
Phase | Description | Raised by | Date Noted | Next Steps | Owner | Target Date | Open / Closed | Days Past Due | Status | Resolution/Comments | Date Closed

## Decisions
ID | Decision Maker | Status | Date Noted | Phase | Decision Description | Date Communicated | Communicated to
1
2
3
4
5
6
7
8
9

## Dependencies
ID | Decision Maker | Status | Date Noted | Phase | Decision Description | Date Communicated | Communicated to
1
2
3
4
5
6
7
8
9

## How to - Issues
Name:
Issues and actions
# | This column is just an ordinal number used to keep track of issue/action items. The number is useful when referencing an item, and helps avoid the need to read out the whole description
Description | This is a relatively brief description of the action item or issue. It should not be a complete paragraph that describes all the detail. It is a headline for summary.
Raised by | A field to identify who raised the issue. This becomes useful when, after a time, the description or origin of the item is not clear.
Date Noted | Used to record when the issue or action was first noted. This helps to understand how much time we had to address an issue or action.
Owner | There should only ONE person identified as the "owner" of an item. While a team may be leveraged to completely resolve an item, only one person should be accountable for owning the result of the action or issue.
Days Past Due | This is a calculated field based on the due date and today's date
Status | This is a calculated field based on the days past due. Tolerance has been set to days late = 5 or less days GREEN 6-10 days late = YELLOW more than 10 days past due = RED These tolerances can be changed by updating the formula and the conditional formatting of the cells
Open / Closed | This is a calculated field based on a close date. If there is a close date, the status is changed to CLOSED; otherwise the status is OPEN
Target Date | A field to record the expected delivery date for an issue resolution or a closed action item.
Date Closed | Actual date item was closed. This field updates the Days past Due, status and Open/closed fields
Resolution/Comments | Please provide any clarifying notes in this field. However, please note that the longer the explanation, the "taller" the row height will be. Caution should be exercised in providing "all" the detail vs. impacting the use of the spreadsheet tool.
Use of Filtering | Each colum of the spreadsheet has a filter "switch" (i.e., a small box with a down arrow) that can be used to clearly show information in the worksheet. Common Filter examples: - Owner: to see all the tasks assigned to one owner, select the filter switch by Owner and highlight the name of the owner you want (all other owners will be hidden) - Open / Closed: to hide all completed or Closed items, select the filter switch by Open/Closed and highlight OPEN and Blank. This will display all un-used rows and all open items, hiding the closed items.

## How to - Risks
Risk management template
EXPOSURE LEGEND
| H | Yellow | Red | Red
Risk Prob | M | Green | Yellow | Red
| L | Green | Green | Yellow
|  | L | M | H
Risk Impact
Risk Probability
High (5) | Greater than 70% probability of occurrence
Medium (3) | Between 30% and 70% probability of occurrence
Low (1) | Below 30% probability of occurrence
Risk Impact
High (5) | Risk that has the potential to have high impact on cost, greatly delay schedule, significantly impair quality or scope
Medium (3) | Risk that has the potential to have some impact on cost, slightly delay schedule, or slightly impair quality or scope
Low (1) | Risk that has relatively little impact on cost, schedule, quality or scope
Risk Response Strategy
Avoid | Change the project plan to eliminate the risk or to protect the objectives of the project from the risk impact
Accept | Accept the risk, document and communicate it, but don't develop a plan to mitigate the risk. Take a chance that it will not occur
Mitigate | Develop a plan to reduce the risk and continually monitor the risk and any identified residual risk
Transfer | Attempt to shift the consequence of risk to a third party
Contingency | Prepare a plan to address the program impacts of the risk if it arises
NOTE: The contingency plan should explain the strategy that will be used to address the risk event should it occur, the time-frame for invoking the contingency plan, who has authority to invoke the contingency plan, and a list of individuals (internal and external) who must be notified that the contingency plan has been invoked.
NOTE: When printing, make sure to update the range of cells to include the entire document
* denotes drop down field, press both the ALT and ENTER key to create a Carriage Return within a cell
Risk Register Field |  | Description
Risk ID |  | A sequential number manually entered into the spreadsheet. This number should be unique to project related risks.
Due Date to Avoid Impact |  | The date the risk must be mitigated to avoid impact.
Risk Driver (drop down) |  | Fundamental drivers that cause risk events. Risk sources are both internal and external to the initiative. They identify common areas where risk may originate. A complete list of typical risk drivers can be found in the Risk Identification section of this document and may also be found in the drop down list in the Risk Register template. If you do not find an appropriate risk driver in the drop down list you may type a new one into the column.
Risk Description and Impact Effect |  | A text description of the risk. The format used should discuss the risk event and the potential consequence / impact effect of the risk.
Risk Probability (drop down) |  | A subjective assessment of the likelihood that the risk will materialize. This should be completed by the Program Manager, with input from the appropriate team members. The selection options are as follows: High Medium, Low.
Risk Impact (drop down) |  | Based on a subjective assessment by the Program Manager, with input from the appropriate team members, and is one of the following categories: High, Medium, and Low.
Risk Score (calculated) |  | The product of the risk probability and the risk impact with values ranging from 1 to 9.
Risk Exposure (calculated) |  | Exposure rating of the risk. The risk exposure is set to the following: Green for risk scores of 1, 2, Yellow for risk scores of 3, 4, and Red for risk scores of 6, 9.
Risk Response Strategy (drop down) |  | Actionable response to the risk. Mitigation strategies are required for yellow and red risk exposures. Selection options are listed below: Avoid - Do not continue with this particular aspect, because the risk is so great that the benefits would not be cost effective; Accept - Accept the risk, document and communicate it, but don't develop a plan to mitigate the risk; Mitigate - Develop a plan to reduce the risk and continually monitor the risk and any identified residual risk; Transfer - Attempt to shift the consequence of risk to a third party; Contingency - Prepare a back-up plan to address the program impacts of the risk if it arises.
Mitigation Response (Contingency Plan) / Action Log |  | A comments field that is to be updated with all activity associated (e.g. mitigation steps, contingency plan, etc.) with the risk. Each response should be accompanied with the date and initials or name of the person adding the comment. Note: The contingency plan should explain: The strategy that will be used to address the risk event should it occur, the timeframe for invoking the contingency plan, who has authority to invoke the contingency plan, and a list of individuals (internal and external) who must be notified that the contingency plan has been invoked.
Owner |  | The person who owns the risk. This individual is responsible for gathering the necessary information to assess the risk and follow-through on mitigation activities. The Program Manager is responsible for assigning the risk owner.
Status (drop down) |  | Indicates the status of the risk. Selection options are: open and closed. The status field is set to closed when either a risk has become an issue or ceases to be a risk.